# Delivery Health & Bottleneck Intelligence Platform: PRD

- Version: 1.0

- Date: July 13, 2026

- Team Size: 2 Engineers

- Timeline: 20 Working Days

## 1. Problem Statement

A remote-first engineering company scatters standup notes, sprint velocity, and blocker updates across separate tools (Slack, Jira, standup bots, docs). Because this data is fragmented, leadership has no single lens to tell whether a slowdown is a temporary coordination hiccup (someone on PTO, a flaky CI pipeline) or a systemic delivery bottleneck (recurring dependency waits, chronic under-resourcing, a broken process).

Without that distinction, leadership either over-reacts to noise or under-reacts to real structural problems, and interventions land in the wrong place.

## 2. Goal

Build a lightweight platform that ingests standup, velocity, and blocker data from multiple sources, classifies issues as transient vs. systemic, and gives leadership a clear, trustworthy view of where real bottlenecks live—without adding new reporting overhead for engineers.

## 3. Success Metrics

- Leadership can correctly identify a systemic bottleneck (validated against a known historical case) using the dashboard alone.

- 80% of blockers are auto-tagged transient/systemic with an explainable reason.

- Time to detect a recurring blocker pattern drops from "anecdotal / weeks" to "visible within 1 sprint."

- Engineers spend zero additional minutes/day on manual reporting (data comes from existing tools).

## 4. Target Users

- Primary: Engineering leadership (VP Eng, Directors, EMs) — need the aggregated, classified view.

- Secondary: Team leads / Scrum masters — need to drill into their team's blockers.

- Not targeted (v1): Individual contributors as active dashboard users (they are a data source, not a consumer).

## 5. Scope

### In Scope (v1)

- Ingestion Connectors: Jira (velocity + issue/blocker data), Slack (standup channel messages), and a simple standup-bot/CSV import as a fallback.

- Normalization Layer: Unify "blocker," "impediment," "waiting on X" language into one schema.

- Classification Engine: Rule-based + simple heuristic scoring to label items Transient vs Systemic, with a recurrence/duration signal (e.g., same blocker type appearing 3+ sprints = systemic).

- Leadership Dashboard: Sprint velocity trend, active blockers by type, transient vs systemic breakdown, team-level drill-down.

- Basic Alerting: Flag when a blocker crosses the systemic threshold.

### Out of Scope (v1)

- Predictive ML models (v2 candidate).

- Two-way write-back into Jira/Slack.

- Mobile app.

- Custom integrations beyond Jira/Slack (e.g., Linear, Asana) — architected for later, not built now.

## 6. Functional Requirements

- F1 (Priority: P0): Pull sprint velocity + issue data from Jira via API

- F2 (Priority: P0): Pull standup/blocker mentions from a designated Slack channel via API

- F3 (Priority: P1): CSV/manual import fallback for teams not on Jira/Slack

- F4 (Priority: P0): Normalize all blockers into a common schema (team, date, description, category, source)

- F5 (Priority: P0): Classify each blocker as Transient/Systemic based on recurrence, duration, and cross-team pattern

- F6 (Priority: P0): Dashboard: velocity trend per team

- F7 (Priority: P0): Dashboard: blocker breakdown (transient vs systemic) with drill-down by team/category

- F8 (Priority: P1): Alert/flag when a blocker recurs beyond threshold (config: default 3 sprints)

- F9 (Priority: P1): Simple auth (leadership login)

## 7. Non-Functional Requirements

- Data refresh at least once/day (near-real-time not required for v1).

- Read-only integrations only (no write access needed $\rightarrow$ lower security risk, faster approval).

- Must not require engineers to change their existing workflow.

## 8. Classification Logic

A blocker is scored Systemic if it meets >2 of the following criteria:

- Same root-cause category recurs across $\ge$3 sprints for a team.

- Same category appears across >2 different teams in the same sprint.

- Average resolution time for that category exceeds a configurable threshold (e.g., >5 days).

- It's explicitly tied to a dependency (another team/system) rather than an individual's availability.

Otherwise, it is classified as Transient (e.g., single mention, resolved in <2 days, tied to PTO/one-off outage).

Note: This keeps v1 explainable—leadership can see why something was tagged systemic, which builds trust before introducing ML later.

## 9. Architecture

Data Sources

|

Jira      Slack       CSV Upload    Future Scaling

│

Ingestion Service

│

Data Validation

│

Data Cleaning Pipeline

│

Normalization & Standardization

│

Feature Extraction Engine

│

┌──────────────┴──────────────┐

Analytics Engine              		Classification Engine

│

PostgreSQL Database

│

Analytics REST API

│

React Dashboard

## 10. Tech Stack

- Backend: Python (FastAPI) — fast to write connectors + scoring logic.

- DB: PostgreSQL (or SQLite for the prototype, swap later).

- Frontend: React + a charting lib (Recharts) — single dashboard app.

- Scheduler: Simple cron job / APScheduler for daily ingestion.

- Auth: Basic email/password or magic link (skip SSO for v1).

- Hosting: Render/Railway/Fly.io for speed — avoid infra overhead with 2 people.

## 11. Team Split

Given the two biggest independent tracks are data (ingestion/classification/backend) and experience (dashboard/frontend + integration polish), split by track rather than by day, so you're not blocked on each other:

- Engineer A - Data & Backend: Jira/Slack connectors, normalization schema, classification engine, DB, API endpoints.

- Engineer B - Product & Frontend: Dashboard UI, auth, alerting UI, PRD-to-demo narrative, plus CSV import fallback (F3) since it's UI-adjacent.

Both pair on schema design (Day 1-2) and on final integration/demo (Day 18-20).

## 12. Execution Plan

### Phase 1 - Foundation

- Day 1

  - Engineer A: Finalize data schema (blockers, velocity, teams) together; set up repo, DB.

  - Engineer B: Same schema workshop; set up Figma/wireframe for dashboard.

- Day 2

  - Engineer A: Jira API auth + pull sprint/velocity data (raw).

  - Engineer B: Wireframe dashboard screens (velocity view, blocker view); set up React skeleton.

- Day 3

  - Engineer A: Slack API auth + pull messages from standup channel (raw).

  - Engineer B: Auth flow (login) scaffolding.

- Day 4

  - Engineer A: Normalize Jira + Slack data into common schema.

  - Engineer B: Build API client layer in frontend (mock data first).

### Phase 2 - Core Logic & UI

- Day 5

  - Engineer A: Build classification engine v1 (recurrence rule).

  - Engineer B: Velocity trend chart (using mock data).

- Day 6

  - Engineer A: Add cross-team + duration rules to classification.

  - Engineer B: Blocker breakdown chart (transient vs systemic).

- Day 7

  - Engineer A: Persist classified blockers to DB; write API endpoints (GET blockers, GET velocity).

  - Engineer B: Connect frontend charts to real API endpoints.

- Day 8

  - Engineer A: CSV import parser (backend side, for F3).

  - Engineer B: Team drill-down view UI.

- Day 9

  - Engineer A: Scheduler: daily ingestion job (cron).

  - Engineer B: CSV upload UI (frontend for F3).

- Day 10 (Joint Milestone)

  - Both Engineers: Mid-point sync/demo: integration test of full pipeline (Jira $\rightarrow$ classify $\rightarrow$ DB $\rightarrow$ API) & Polish dashboard layout, empty/loading states.

### Phase 3 - Hardening

- Day 11

  - Engineer A: Alert threshold logic (config + trigger).

  - Engineer B: Alert banner/notification UI on dashboard.

- Day 12

  - Engineer A: Config UI backend (thresholds editable).

  - Engineer B: Auth backend integration (real login, sessions).

- Day 13

  - Engineer A: Error handling + logging across connectors.

  - Engineer B: Team/category filter UI on dashboard.

- Day 14

  - Engineer A: Rate-limit handling + retry logic for Jira/Slack APIs.

  - Engineer B: "Why is this systemic?" explainability panel (shows the 4 rule signals).

- Day 15

  - Engineer A: Write tests for classification engine (edge cases).

  - Engineer B: Responsive/UI polish pass.

### Phase 4 - Final Demo

- Day 16

  - Engineer A: End-to-end test with real (or realistic seeded) data across 3+ sprints.

  - Engineer B: End-to-end UI walkthrough with real data.

- Day 17

  - Engineer A: Bug fixing from E2E test.

  - Engineer B: Bug fixing from UI walkthrough.

- Day 18

  - Engineer A: Deploy backend + DB to hosting.

  - Engineer B: Deploy frontend, connect to live backend.

- Day 19 (Joint Milestone)

  - Both Engineers: Full regression pass, fix deployment issues.

- Day 20 (Joint Milestone)

  - Both Engineers: Prep demo narrative, walk through sample data, final PRD/README polish.

## 13. Risks & Assumptions

- Assumption: Jira and Slack API access/credentials can be obtained quickly (day 1-2) — if not, this is the biggest schedule risk; have CSV import as fallback demo path.

- Risk: Classification rules may need tuning after seeing real data — budget buffer inside Days 15-17 for this.

- Risk: With only 2 people, scope creep is the main threat - hold the line on "out of scope" list above until v1 ships.

- Assumption: One Slack channel per team is used consistently for standups (if not, ingestion gets messier - worth confirming with pilot teams before Day 3).

## 14. Definition of Done

Leadership can log in, see velocity trend + blocker breakdown for at least 2 real (or seeded) teams across 3+ sprints, and see a clear, explainable transient/systemic tag on each blocker.